## Story Points
Story Points (Fibonacci Scale) |  |  |  | Points By Week
Scale: 0.5, 1, 2, 3, 5, 8, 13, 15
Story Name | Jon | Anthony | Average | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
EPIC | 0 | 0 | 0 | 8.5 | 12 | 5 | 11 | 8 | 10 | 4 | 11.5 | 19 | 0 | 6.5 | 0 | 12.5
Login Process | 1 | 1 | 1
FrontEnd User Login Screen | 3 | 5 | 4
Update Admin Info | 2 | 1 | 1.5
FrontEnd Create User Account | 5 | 5 | 5
Retrieve Data (Remote Setup) | 5 | 2 | 3.5
View Employee Data | 1 | 2 | 1.5
View Admin Data | 3 | 2 | 2.5
BackEnd Create User Account | 5 | 1 | 3
Save Picture Links for the Types of Users | 1 | 1 | 1
Create Under Construction Page | 5 | 8 | 6.5
Connecting to Database | 3 | 5 | 4
Unique Barcode display | 1 | 1 | 1
Successful Login/Logout Pages | 3 | 5 | 4
Conceal SQL Statements | 3 | 1 | 2
Locked Account Page | 3 | 1 | 2
Incorrect Input Page | 1 | 3 | 2
Lock User Accounts | 3 | 1 | 2
Reset Attempts | 1 | 3 | 2
Reset Locked Accounts | 3 | 5 | 4
Secure Hash Algorithm | 1 | 3 | 2
Store Account Data | 1 | 1 | 1
User Login Screen | 1 | 1 | 1
Print User Results | 1 | 1 | 1
View Work Table | 1 | 1 | 1
Create User Account | 2 | 2 | 2
Responsive Webpage | 3 | 5 | 4
Display Output | 3 | 1 | 2
Registration Error | 1 | 1 | 1
Registration Notification | 5 | 8 | 6.5
Secure Website | 8 | 5 | 6.5
Admin Task List | 5 | 3 | 4
Store Time Data | 2 | 1 | 1.5
Error Redirects | 3 | 5 | 4
Content Security Policy | 5 | 3 | 4
Main System Logout | 1 | 1 | 1
Automatic Emailing | 13 | 13 | 13
Admin Clock-In | 2 | 2 | 2
Total | 109 | 109 | 109

## Points By Week
Points By Week
Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13
10 | 10 | 6 | 10 | 10 | 9 | 5